## P6_Export
Activity ID | Activity Name | Original Duration (days) | Predecessors
A1000 | MEP & E&I Installation | 40 |  | ← 範例資料：貼上你自己的 P6 匯出時請整批覆蓋（從 A2 開始貼）
A1010 | L3 Power Distribution PFT | 8 | A1000
A1020 | L3 Cooling Systems PFT | 8 | A1000
A1030 | L4 Power Distribution FPT | 12 | A1010
A1040 | L4 Cooling Systems FPT | 15 | A1020
M1000 | Ready for IST (Milestone) | 0 | A1030, A1040
A1050 | L5 Integrated Systems Test | 20 | M1000

## Activities
id | name | predecessors | dist_type | param_a | param_m | param_b | param_mu | param_sigma | deterministic_duration
A1000 | MEP & E&I Installation |  | triangular | 36 | 40 | 52
A1010 | L3 Power Distribution PFT | A1000 | triangular | 7.2 | 8 | 10.4
A1020 | L3 Cooling Systems PFT | A1000 | triangular | 7.2 | 8 | 10.4
A1030 | L4 Power Distribution FPT | A1010 | triangular | 10.8 | 12 | 15.6
A1040 | L4 Cooling Systems FPT | A1020 | triangular | 13.5 | 15 | 19.5
M1000 | Ready for IST (Milestone) | A1030;A1040 | deterministic | 0 | 0 | 0
A1050 | L5 Integrated Systems Test | M1000 | triangular | 18 | 20 | 26

## RiskDrivers
id | name | probability | impact_type | impact_a | impact_b | impact_m | assigned_activities
RD-001 | Vendor Equipment Delay | 0.35 | triangular | 1 | 1.4 | 1.15 | A1010;A1020
RD-002 | Commissioning Staff Availability | 0.25 | triangular | 1 | 1.3 | 1.1 | A1030;A1040;A1050

## 說明
Converge P6 匯入範本 — 使用說明
■ 操作步驟（你只需要碰 P6_Export 和 RiskDrivers 兩張表）
1. 從 P6 匯出 Excel，整理成四欄：Activity ID、Activity Name、Original Duration、Predecessors。
2. 貼到 P6_Export 工作表（從 A2 開始，覆蓋範例資料）。Activities 表會全部自動產生，不要手動改它。
3. 檢查 Predecessors：本範本自動把逗號轉成分號、移除空格。若 P6 匯出含 lag 或 SS（如「A1000: FS+5d」），
請在 P6_Export 中手動改成 Converge 格式：A1000:FS:5（FS 加 5 天 lag）、A1000:SS:3（SS 加 3 天 lag）。
4. 在 RiskDrivers 表填風險驅動因子（這是 QRA 的核心輸入，P6 沒有的資訊）。
5. 存檔 → 開 Converge App → Data Input 分頁 → Import Activities / Import Risk Drivers，選這個檔案。
■ dist_type 是什麼？（P6 沒有這個欄位，這是正常的）
它是「工期不確定性的形狀」。注意：這和你熟悉的 PERT 圖（網圖）是兩回事，只是撞名——
這裡的 pert 指 Beta-PERT 機率分布。P6 是確定性工具，每個活動只有一個工期；QRA 補上的正是「工期會怎麼變動」。
本範本預設全部用 triangular（三角分布，業界標準起點），0 工期的里程碑自動設為 deterministic。留空匯入也會自動當 triangular。
■ 格式限制（務必遵守）
． 工作表名稱不可改：P6_Export / Activities / RiskDrivers。Activities 的欄位標題列不可改。
． Original Duration 必須是純數字（工作天），不可帶單位文字（如「10d」）。里程碑填 0。
． 不要包含 WBS / summary / LOE 列——只貼真正的活動與里程碑。
． Activity ID 不可重複；Predecessors 引用的 ID 必須存在。
樂觀係數（param_a = Duration ×） | 0.9 | 建議起步值
悲觀係數（param_b = Duration ×） | 1.3 | 右偏：延誤空間 > 提早空間
這些係數只是初始假設。正式分析請以 duration ranging workshop 的專家判斷逐活動覆寫 Activities 表的 param_a / param_b
（覆寫＝把該格公式改成數值即可）。高風險活動（首次施作、許可審批、長交期設備）特別要加大 param_b。